May 21, 2025

| Dane Servatius |  |
| --- | --- |
| Power and Recovery Maintenance Planner |  |
| * : | Kruger Kamloops 2005 Mission Flats Road, Kamloops, BC, V2C 1A9 |
| @ : | Dane.Servatius@kruger.com |
| cc: | Mark.Eppler@kruger.com |

Proposal no SO-25610-KAM Rev 1

Technical Supervision TG-A stator replacement

Mr. Servatius,

Following your recent email we are pleased to submit this revised proposal for technical supervision of the TG-A stator replacement project. Please find below the scope of work, details, and conditions of our proposal as well as our price, calculated on a Time and Material basis as per our Rates Sheet, attached in Appendix A and our Terms & Conditions attached in Appendix B. Please note that preparation, report phases will be charged at fixed price.

# Budgetary Estimate

Rev 1

$160 800,00

One hundred and sixty thousand eight hundred Canadian dollars

Proposed options

| Option 1: | Replacement resource during turn-around | $23 400,00 |
| --- | --- | --- |

Rev 1

Mandate Description

| Working Hours: | 12 hr/day – 7 d/week |  |
| --- | --- | --- |
| Turn Around Schedule: | We are planning to have 5 days rotation in order to ensure that the resource provided respects our internal continuous site work policy. Replacement of this resource during the turn around is priced as an option depending on the project needs |  |
| Schedule: ** | Work Beginning Date: August 4th 2025 Expected Duration: 30 days |  |
| Crew: | Qty 1 1 | Role Night shift TFA Night shift Technical Supervisor (rotation with overlap) |
| Accommodation: | Type 2 (Appendix A – Rates 2025) |  |
| Report: | Type 4 (Appendix A – Rates 2025) |  |
| Special Conditions | N/A |  |

** Any date change for work performed less than one month before project starting will result in an extra fee of 5% of the project cost.

Rev 1

Scope of Work

| ###### Work included | ###### Estimated ###### men-hours |
| --- | --- |
| Travelling to and from site | 48+24 |
| Night shift TFA to supervise the stator replacement work in collaboration with Ake Tengvall | 300+84 |

| ###### Optional Work | ###### Estimated ###### men-hours |
| --- | --- |
| Option 1: Replacement during turn around (Technical supervisor) - Travelling to and from site - Night shift Supervision on the stator replacement work | 96 |

# Division of Responsibilities

| ###### Description |  | N/A | Enerserv | Client |
| --- | --- | --- | --- | --- |
| ###### Project Resources |  |  |  |  |
| Project Manager/Site Manager |  |  |  | X |
| Technical Field Advisor (night shift) |  |  | X |  |
| Quality Control Technicians |  |  |  | X |
| Health, safety, and environment on site Supervisor |  |  |  | X |
| Working Foreman |  |  |  | X |
| Labour to execute the work |  |  |  | X |
| Winders |  | X |  |  |
| Electricians/Technician for electrical equipment disconnection & reconnection |  |  |  | X |
| Overhead crane operator |  |  |  | X |
| Mobile equipment operator |  |  |  | X |
| Labour for insulating blankets removal and installation |  |  |  | X |
| Technician for instrumentation disassembly and reassembly |  |  |  | X |
| Instrumentation calibration technician |  |  |  | X |
| Partial Discharge and electrical testing technician |  | X |  |  |
| Non-Destructives testing technician (NDT) – PT, MT, UT |  |  |  | X |
| Confined space Supervisors |  |  |  | X |
| ###### Specialized Resources |  |  |  |  |
| Engineer |  | X |  |  |
| Vibration Specialist |  | X |  |  |
| Geometric Alignment Specialist (FARO) |  | X |  |  |
| Tribology Specialist |  | X |  |  |
| Speed Control (governor) Specialist |  | X |  |  |
| Protection relay Specialist |  | X |  |  |
| Commissioning Specialist |  |  |  | X |
| Electrical Specialist for testing and inspections |  | X |  |  |
| ###### Safety and Training |  |  |  |  |
| Equipment lockout & tagout |  |  |  | X |
| Daily safety meeting (Toolbox/FLHA) |  |  |  | X |
| Personal Protection Equipment, standard |  |  | X |  |
| On site safety training for labour |  |  |  | X |
| FME area and installation/dismantling of safety fences |  |  |  | X |
| Confined space rescue team |  |  |  | X |
| First aid and rescue team on site |  |  |  | X |
| Fire extinguishers available on work site |  |  |  | X |
| ###### Equipment and Tools |  |  |  |  |
| Standard tooling including metrology and other necessary equipment for execution of the project (list available on demand) |  |  |  | X |
| Specialized tooling supplied by EnerServ: |  | X |  |  |
| Specialized tooling (OEM): |  |  |  | X |
| - Alignment special tooling |  |  |  |  |
| Mobile equipment |  |  |  | X |
| Blocking |  |  |  | X |
| Floor protection |  | X |  |  |
| Supplementary lighting (outage, poor lighting) |  |  |  | X |
| ###### Logistics |  |  |  |  |
| Insurance for customer's components during transportation to/or during off-site workshop work |  | X |  |  |
| Custom logistics and fees if applicable. If by Enerserv, the owner may be required to provide assistance or documentation, as necessary, given their ownership of the shipped component. |  | X |  |  |
| Transportation of parts for rebuild |  | X |  |  |
| Quality oversight of shop work |  | X |  |  |
| Lodging, per-diem, travelling for our TFA |  |  | X |  |
| On site preparation before outage |  | X |  |  |
| ###### Facilities |  |  |  |  |
| Area/trailer for workers |  |  |  | X |
| Office area or on-site trailer |  |  |  | X |
| Sanitary facilities (toilet and sink) |  |  |  | X |
| Area for parts inspection and cleaning |  |  |  | X |
| ###### Work in the presence of hazardous materials |  |  |  |  |
| Asbestos decontamination |  | X |  |  |
| Trash disposal including hazardous materials |  |  |  | X |
| Lead paint removal |  | X |  |  |
| Installation and maintenance of a pressure-controlled zone |  | X |  |  |
| Specialized Personal Protection Equipment |  | X |  |  |
| ###### Rigging & Work at Height |  |  |  |  |
| Rigging plan |  |  |  | X |
| Engineered/stamped lifting plan |  | X |  |  |
| Standard rigging & slinging (lanyard, slings, shackles, etc.) |  |  |  | X |
| Scaffolding |  |  |  | X |
| Mobile crane service |  | X |  |  |
| ###### Parts & Consumables |  |  |  |  |
| Standard consumables (list available upon request) |  |  |  | X |
| Spare parts and component specific consumables |  |  |  | X |
| Oil, glycol, nitrogen, and other operation fluids |  |  |  | X |
| ###### Permits |  |  |  |  |
| Work permit |  |  |  | X |
| Confined space |  |  |  | X |
| Hot work |  |  |  | X |
| ###### Telecommunications |  |  |  |  |
| High-speed Internet connection or wireless (applicable fees if provided by EnerServ) |  |  |  |  |
| On site Broadband Radio |  |  |  |  |
| ###### Utilities |  |  |  |  |
| Dry and High flow compressed air (185CFM) |  | X |  |  |
| Electrical power (120V/240V single phase & 600V three-phase) |  |  |  | X |
| Supplementary electrical power (in case of outage) |  |  |  | X |
| Compressed air (for small tools) |  |  |  | X |
| Water access (drinkable or not) |  |  |  | X |
| ###### Quality |  |  |  |  |
| Inspection/measurement of new or refurbed components supplied by client or other parties |  |  |  | X |
| ###### HSE Documentation (to be provided prior mobilization) |  |  |  |  |
| Site and scope specific lock-out and tag-out procedure |  |  |  | X |
| Site specific emergency and rescue procedures |  |  |  | X |
| List of site specific HSE requirements (trainings, PPE, etc) |  |  |  | X |
| Noise exposure assessment/noise control and hearing conservation program if available |  | X |  |  |
| Existing or known confined space and work at height hazard assessment, including but not limited entry and rescue procedures. |  |  |  | X |
| Inspection report and certificate of acceptance for overhead cranes and other permanent lifting equipment |  |  |  | X |
| ###### Technical Documentation (to be provided prior mobilization) |  |  |  |  |
| Previous inspection reports |  |  |  | X |
| All available technical manuals, in PDF or paper format, for the equipment to be serviced |  |  |  | X |
| List of material / components that will be supplied by the client |  | X |  |  |
| Inspection and test plan (ITP) |  |  |  | X |

## Clarifications

- All components are presumed to be in good condition, and the disassembly schedule and costs have been estimated using available drawings and technical details available at the time of the proposal. Actual time and costs may vary based on the component's "as-found" condition.  Any discovery work will be classified as a Defect (AN) and presented to the customer along with recommended solutions for their review and disposition.

- The proposed schedule and costs are based on the work outlined in the "Scope of Work" section, in alignment with the proposed workweek schedule. It assumes that the customer will provide all necessary resources and support according to the same workweek schedule, including but not limited to the overhead crane and the items listed in the division of responsibility table.

- Unless specified otherwise, a full disassembly is not typically part of our inspection process. The primary goal is to ensure that each component functions properly before it is returned to service, avoiding unnecessary disassembly of components in working order. Full disassembly of specific components can be performed upon request once the required spare parts are confirmed to be onsite.  All spare parts are the customer’s responsibility unless explicitly specified in the DOR

# Health, Safety and Environmental Training and Activities

Health and safety are our top priorities. Given that we serve customers across Canada with diverse requirements, we have standardized a set of core competencies and trainings for our crew according to industry standards.

Additionally, we conduct standard HSE activities to ensure ongoing safety compliance and risk management. Our activities consist of:

- Field Level Hazard Assessment

- Daily Toolbox meeting

- Pre-use inspections

- Weekly site inspections

- Weekly safety meetings

These practices help maintain essential safety standards across various environments. If the customer requires additional training or HSE activities to meet specific site or regulatory needs, it can be arranged as necessary.

# Cost Breakdown (excluding options)

Rev 1

Cop the et (EXPORT ABAK, right side). Delete unused lines.

| Project Preparation & closure (off site) | $ 800,00 | Fixed Price |
| --- | --- | --- |
| Engineering | $ 0,00 |  |
| Project off site technical support (off site) | $ 0,00 |  |
| Traveling* (3 round trips from Granby) | $ 20 300,00 |  |
| Site Work** | $ 127 200,00 |  |
| Sub-Contractors | $ 0,00 |  |
| Site purchases & external rentals*** | $ 0,00 |  |
| Report | $12 500,00 | Fixed Price |
| Total | $ 160 800,00 |  |

* Travel costs include rotations, mileage and airfare where applicable.

** Amount for on-site work includes, accommodation, per diem and Enerserv owned tooling.

*** Includes shipping of tools.

# Our Insurance

| Type of insurance | Limits |  |
| --- | --- | --- |
| Type of insurance Commercial general liability Contractual liability Contingent employer liability | Each occurrence | $5 000 000 |
|  | Personal injury | $5 000 000 |
|  | Products & Completed operations aggregate | $5 000 000 |
|  | Tenants Legal liability | $250 000 |
| Rigger liability including third party |  | $25 000 |
| Owned and non-owned automobile liability | Automobile liability limit | $5 000 000 |
| Professional liability | Each claim and aggregate | $2 000 000 |
| Broad form environment impairment liability | Each claim and agg. | $ 5 000 000 |
| Third party property insurance | Covers customer's property during transportation by EnerServ and work at EnerServ's facility | $ 500 000 |

Note:     Enerserv can provide a certificate with mention of additional insured, if required. 
Any other additional insurance is excluded, but can be added at customer's request (Fees apply)

# Terms of payment

All invoices are payable Net 30 days

Time and Material Projects:

Advance Payment:  20% will be invoiced 60 days before mobilization

Separate invoices may be issued for:

- Project Preparation off site: Billed as a fixed price

- Site cost: Hours worked, per diem, accommodation, tooling etc. (billed every 2 weeks)

- Expenses & Materials: Includes material, subcontractors and other expenses (billed monthly)

- Report (if applicable): Billed separately as required

Note: No holdbacks will be accepted.

Mr. Servatius, should you accept our offer, please provide a purchase order referencing the project number listed on the front page and return a signed copy of this offer letter.  The terms and conditions included in Appendix B are an integral part of this proposal and take precedence over any other document issued by either parties subsequent to the acceptance of this proposal by issuance of a Purchase Order unless otherwise agreed by the parties.

We appreciate the opportunity to present our proposal and look forward to the possibility of working with you in the near future.

Best regards,

|  |  | Date: | May 21, 2025 |
| --- | --- | --- | --- |
| Prepared by: | Bruno Girard, P.Eng. |  |  |
|  | Enerserv inc. |  |  |
|  |  | Date: | May 21, 2025 |
| Reviewed by: | Rémy Poirier, P.Eng. |  |  |
|  | Enerserv inc. |  |  |
| Received and accepted by: |  | Date: |  |
|  | Dane Servatius |  |  |
|  | Kruger |  |  |

This offer is valid for a period of 30 days.

Rates presented are applicable until December 31, 2025.

##### Do not delete the section break

Appendix List

APPENDIX A Rates 2025	11

APPENDIX B Terms & Conditions	12

APPENDIX A
Rates 2025

APPENDIX B
Terms & Conditions